## How to use
Risk Matrix
Risk matrix, consequence criteria, likelihood scale and control hierarchy. A working template from Streamline ISO Consultants.
streamline.business ¦ hello@streamline.business ¦ Brisbane 07 3667 8280 ¦ Sydney 02 8315 7780 ¦ Melbourne 03 9034 3990
What this template is for
A risk score only means something when it is measured against criteria somebody wrote down. This workbook holds the four pieces that make a matrix usable: a consequence scale per discipline, a likelihood scale with a stated basis, a ranked matrix, and a rule about what happens at each band and who may accept it.
Fill in the yellow cells first. They are the ones only you can answer.
Every yellow cell carries a worked sample, shown in italics. The samples exist to demonstrate the calibration, not to be adopted: the financial bands, the likelihood basis and the acceptance authorities are the three settings that make a matrix yours rather than a download, and getting them wrong quietly breaks everything else. Replace them before the workbook is used in anger.
Why the cells are ranked 1 to 25 rather than multiplied
Multiplying likelihood by consequence produces ties between events that are not equivalent. A rare catastrophe and a frequent nuisance can reach the same product and they need completely different responses. Ranking every cell forces the order to be decided deliberately, and it lets a register be sorted into a priority list rather than four coloured piles.
One likelihood scale, several consequence scales
The consequence sheet carries a column per discipline. A single axis written for injuries cannot meaningfully score a defect, a spill, a data breach or a wrong automated decision. Calibrate the columns against each other so that a level 4 means the same weight of bad day whichever one it sits in.
Information security and AI are in the core, not the tail
Almost every business now holds personal information and runs software that shapes decisions about people. Both carry statutory consequence paths: the notifiable data breach scheme, and from 10 December 2026 the automated decision-making transparency requirements in APP 1.7 to 1.9.
Which hierarchy of controls this workbook uses
The Hierarchy of Controls sheet uses the five items in ISO 45001 clause 8.1.2. That is the agreed international expression, it is what a certification auditor reads, and it travels across jurisdictions. Australian model WHS Regulation 36 covers the same ground with a different carve-up: it names isolation separately and treats substitution, isolation and engineering controls as one minimisation tier rather than ranking them. The six-rung ladder on most site posters matches neither exactly. Pick one, state which in your documents, and apply it consistently.
The tail is yours to set
The last four columns of the consequence sheet, property and financial, schedule, quality and performance, are the ones that vary most between businesses and between contracts. They carry a worked sample so you can see the calibration, but the financial bands in particular should be set against your own turnover and balance sheet before anyone scores a risk with them.
A fifteen minute test that produces a real finding
Take three closed risks from your register. Hand them to two people separately and ask each to score likelihood and consequence from these criteria. If the scores differ, the problem is the criteria rather than the people, and that is the finding.
Where the standards ask for this
ISO/IEC 27001 clause 6.1.2 requires risk criteria including risk acceptance criteria. ISO/IEC 42001 clauses 6.1.2 and 6.1.4 cover AI risk assessment and the AI system impact assessment. ISO 45001 clause 6.1.2.2 covers assessment of OH&S risks. ISO 14001 clause 6.1.2 covers significance criteria. ISO 9001 clause 6.1 prescribes no method, which is why the quality column is usually the weakest one on the page.
How to use this file
• Cells shaded pale yellow, with the text in italics, are worked samples for you to replace.
• The descriptors supplied are a worked starting point, not a standard. Edit them to your business.
• Keep one set of criteria across every standard you run. Separate matrices that disagree are found by opening two documents.
Disclaimer
This template is general guidance, not legal or compliance advice, and does not create or replace any obligation under work health and safety, privacy or other law. Check the requirements that apply to your business.

## Risk Matrix
Risk Matrix: likelihood against consequence, every cell ranked 1 to 25
Read the rating word and the rank together. The rank is what lets you sort a register into a priority order, because two cells can share a rating and still not be equally urgent. Cell 15 and cell 11 are both Medium, and 15 outranks 11: a rare catastrophe is treated as more pressing than a frequent nuisance. That ordering is a decision, and it is yours to change.
CONSEQUENCE
LIKELIHOOD | C1 Minor | C2 Moderate | C3 Serious | C4 Major | C5 Catastrophic
L5 Almost certain | Medium 11 | High 16 | Extreme 20 | Extreme 23 | Extreme 25
L4 Likely | Low 7 | Medium 12 | High 17 | Extreme 21 | Extreme 24
L3 Possible | Low 4 | Medium 9 | Medium 13 | High 18 | Extreme 22
L2 Unlikely | Low 2 | Low 5 | Medium 10 | Medium 14 | High 19
L1 Rare | Low 1 | Low 3 | Low 6 | Low 8 | Medium 15
When assessing risk and developing controls, give consideration to (but not only to):
• The realistic likelihood of an event, based on previous incidents and experience
• The nature of the work and the hazard
• What is reasonably practicable
• The amount of control and influence you are able to apply
• Suggestions and incident reports from the industry and from the workforce
• Mandatory requirements in legislation, standards and codes of practice

## Hierarchy of Controls
Hierarchy of Controls: the five items in ISO 45001 clause 8.1.2
Items 1 to 3 control the hazard. Items 4 and 5 control the person, and depend on human behaviour holding up on the worst day rather than the best one. Note that reorganisation of work sits at item 3 with engineering controls, not down at item 4: changing when or how work is done ranks above writing a procedure about it. Tag every control in your SWMS with its item number.
Item | Control type | What it means in practice | What it usually moves
1 | Eliminate the hazard | Remove it entirely. Do not do the task, or design it out before it reaches site. | Likelihood and consequence together
2 | Substitute with less hazardous processes, operations, materials or equipment | Same job, less energy available to do harm. A lower working height, a lighter load, a lower operating pressure. | Mainly consequence
3 | Engineering controls and reorganisation of work | Physical change to plant or process, and change to how and when work is arranged: guarding, interlocks, ventilation, extraction, suppression, barriers, exclusion zones, separation of people from plant, sequencing and rostering. | Mainly likelihood. Guarding and separation can do both.
4 | Administrative controls, including training | Procedures, permits, instruction, supervision, signage. | Likelihood only. A procedure does not change what happens when it is not followed.
5 | Adequate personal protective equipment | The last line, and the only one that fails quietly. | Usually consequence at the point of contact, and nothing at all to likelihood.
Note | Australian model WHS Regulation 36 carves this up differently: eliminate, then minimise by substitution, isolation or engineering controls (used singly or in combination and not ranked against each other), then administrative controls, then PPE. Isolation is named there and is not named in the standard, where it sits inside item 3. Same intent, different grouping. Use the standard's five if you are certified, and keep the regulation in mind as the duty a court applies.

## Consequence Criteria
Consequence Criteria: one scale per discipline, calibrated against each other
A level 4 should mean the same weight of bad day whichever column it sits in. The yellow columns are filled with a worked sample in italics, pitched at a business turning over a few million dollars a year. They are the columns that belong to your business and your contract, so read them as a demonstration of the calibration and then replace them.
Level | Injury and harm | Environment | Information security | AI and automated decisions | Property and financial | Reputation | Legislative | Schedule | Quality | Performance
C5 Catastrophic | Fatality or life-changing permanent disability. Prosecution likely. | Serious harm, immediate or long term, with potential for regulator prosecution. | Large-scale compromise of sensitive or personal information with serious harm likely. Regulator investigation, or an event halting operations. | Systemic incorrect, unsafe or discriminatory automated decisions affecting people's rights. Loss of human oversight of a system with real-world effect. | Loss above $500,000, or damage that stops the business trading. Cannot be absorbed without borrowing or a call on the shareholders. | Public or media coverage, or removal from an approved supplier list. Affects your ability to win work regardless of which customer was involved. | Externally identified and prosecuted. | Delay of a scale that ends the contract, or the project is abandoned. | Systemic defect requiring recall or replacement across several customers. Certification suspended or withdrawn. | Sustained failure against the contracted service levels. Grounds for termination or removal from the panel.
C4 Major | Lost time injury of several days or more, with potential for permanent disability. Prosecution possible. | Off-site impact affecting neighbouring property or water. Regulator infringement notice. | Eligible data breach notified to the regulator and to affected individuals, or extended loss of a business-critical system. Customer data involved. | A pattern of wrong decisions affecting multiple people, or a system operating outside its approved purpose without anyone noticing. | $100,000 to $500,000. Absorbs the year's profit. Recoverable, but the budget for everything else goes with it. | Adverse awareness spreading beyond your customer base into the industry. Prequalification, panel membership or tender scoring affected. | Multiple externally identified infringement notices. | Critical path delayed beyond the contractual float. Liquidated damages payable and the completion date moves. | Defect escaping to the customer and requiring rework at their site, or a major nonconformity raised at audit. | Contracted service level breached across a reporting period. Formal performance review, or a rebate payable.
C3 Serious | Lost time injury of a few days. | Localised impact contained within the site boundary. Reportable, with infringement potential. | Unauthorised access to or loss of personal information affecting a small number of people, or loss of a business-critical system for part of a day. | An automated or AI-assisted decision about a person is wrong and has to be reversed. Complaint or remediation required. | $25,000 to $100,000. A visible hit to the year, covered by deferring planned spend. | Dissatisfaction across several customers, or a performance issue escalated to a client's management. Puts a renewal or a referral at risk. | Externally identified breach, infringement notice received. | Critical path delayed. Recoverable only by acceleration, overtime or extra resources at your cost. | Defect found by the customer on delivery and rejected. Rework at your cost, or a minor nonconformity at audit. | Contracted service level breached once. Corrective action plan requested by the customer.
C2 Moderate | Injury requiring medical treatment, no restricted duties. | Minor impact, immediate containment, no regulator notification. | Unauthorised access to internal information that is not sensitive, or brief loss of a non-critical system. No personal information involved. | Incorrect output used internally and corrected before it reached anyone outside the business. | $5,000 to $25,000. Absorbed inside the existing budget, with a variance to explain. | Formal complaint from one customer requiring a written response and corrective action. Relationship recoverable. | Externally identified breach, warning issued. | A non-critical activity delayed. Absorbed by float, completion date unaffected. | Defect found by internal inspection before dispatch and reworked inside the process. | An internal target missed while the contracted level is still met. Explained in the monthly report.
C1 Minor | Minor first aid or minor illness. | Negligible or temporary inconvenience, no notification. | Security event with no information affected, contained internally. | Incorrect output caught before use. No decision affected. | Under $5,000. Absorbed in normal operating cost. No approval needed. | Concern raised by one customer and closed out directly. No effect on the relationship. | Internally identified potential breach, resolvable in-house. | Minor delay within the day's programme, made up inside the same week. | Minor deviation corrected at the workstation. No rework, and no record beyond the inspection sheet. | Variation inside the normal range. Noted in the trend, no action required.
Note | Set the financial bands against your own turnover and balance sheet, then read across: a fatality and your C5 dollar figure should feel like the same weight of bad day. If they do not, one of the two columns is wrong. The sample bands here are illustrative only. Do not use the same adjective at three levels; if C3, C4 and C5 all say "major", two assessors will split them differently every time.

## Likelihood Scale
Likelihood Scale: attach a probability, and state the basis
The argument about whether something is possible or likely cannot be settled with words. A probability settles it, but only against a stated basis. Choose one basis for the whole matrix, write it in the yellow cell, and use it consistently. Two assessors working to different bases will produce different scores from the same facts and never work out why. The yellow cells below carry a worked sample in italics.
Level | Descriptor | Probability | Notes and worked examples
L5 Almost certain | Common or repeating occurrence | 1 in 10 | Has happened here more than once and nothing has changed since. A manual handling strain in a picking team, or a phishing email reaching an inbox.
L4 Likely | Known to occur, or it has happened here | 1 in 100 | Has happened here once, or happens routinely across the industry. A reversing incident in a busy yard.
L3 Possible | Could occur | 1 in 1,000 | No history here, but a credible path exists and the industry reports it. A fall from a mobile platform that is being used correctly.
L2 Unlikely | Not likely to occur, remote | 1 in 10,000 | Would need a control to fail and the failure to go unnoticed. A guard defeated and the machine then started.
L1 Rare | Practically impossible | 1 in 100,000 | Would need several independent controls to fail at the same time. Collapse of a structure that is certified and inspected.
Basis for these probabilities | Per person, per year of exposure to the task. Chosen because our work is continuous rather than campaign based, and because it lets a hazard faced daily be compared with one faced at a single annual shutdown. Every likelihood in this workbook is read against this basis, and changing it means rescoring the register.

## Actions and Authority
Action Required at each band, and who may accept the residual risk
This is where appetite stops being a philosophy and becomes a control. State the target as well as the bands: controls are developed using the hierarchy to bring residual risk down to Low. Then name the authority, and make it independent, because an acceptance signed by the person carrying the schedule pressure is a formality rather than a decision. The yellow cells carry a worked sample in italics; the job titles are yours to set.
Rank | Rating | What has to happen | Who may accept it
20 to 25 | Extreme | Work does not commence. Additional controls are required to reduce the score. | Nobody. Work does not start. The Managing Director may authorise a different method, not an acceptance of this score.
16 to 19 | High | Documented safe work method statement prepared by the supervisor and approved by management. Prestart meeting, confirmation of controls and responsibilities, progress monitored. | Managing Director, in writing, and only once everything above item 4 of the hierarchy has been shown to be not reasonably practicable.
9 to 15 | Medium | Documented safe work method statement prepared before work starts. The supervisor confirms the crew understands and implements the controls. | Operations Manager or equivalent, in writing. Must not be the person carrying the schedule or the budget for the job.
1 to 8 | Low | The supervisor reviews the task with the crew at prestart. | Supervisor, at prestart, recorded on the sign-on sheet.
Target | Controls are developed using the ISO 45001 clause 8.1.2 hierarchy to reduce the residual risk to Low. Where that is not reasonably practicable, the reason is recorded and the acceptance is signed at the authority level named above. A control at item 4 or 5 is not wrong in itself. It is wrong when the record does not show the items above it were considered and ruled out.