## How to use
Inspection and Test Plan (ITP) Template
A working template from Streamline ISO Consultants
streamline.business ¦ hello@streamline.business
What an ITP is for
An ITP is the quality equivalent of a SWMS. A SWMS plans how high-risk work will be done safely; an ITP plans how the work will be checked so it meets the drawings, the specification and the client’s requirements. It sets out each inspection and test, the acceptance criteria, who checks it, how often, and where work must stop until it is released.
Point types used in this template
• H — Hold point: work must not proceed past this point until the nominated person has inspected and released it in writing.
• W — Witness point: the client or superintendent is given notice and may attend. Work can proceed if they choose not to.
• I — Inspection point: an internal check by the contractor, recorded on the ITP or a referenced checklist.
• R — Review point: a review of documents or records, such as test certificates, delivery dockets or survey results.
How to use it
1. Copy the ITP sheet for each work activity or lot (for example, one ITP for footings, one for kerb and gutter).
2. Complete the header: project, client, activity, ITP number and revision, and the specifications and drawings that apply.
3. Replace the grey example rows with the inspections and tests your specification requires. Yellow cells are for you to fill in.
4. Take the acceptance criteria, test methods and frequencies from the contract specification and the standards it calls up. Do not guess them.
5. Agree the hold and witness points with the client or superintendent before work starts, and how much notice they need.
6. Sign off each line as the work is done, and file the supporting records (test results, photos, survey) against the item number.
7. Close out the ITP when the activity is complete. A signed ITP with its records is the evidence that the work was built to specification.
Where it fits in ISO 9001
ITPs support ISO 9001 clause 8.5 (control of production and service provision) and clause 8.6 (release of products and services). Nonconforming results go through your nonconformance and corrective action process (clause 8.7 and 10.2).
This template is a general example. Check every criterion and frequency against your project specification. Free to use and adapt.

## ITP
Inspection and Test Plan (ITP) ¦ Streamline ISO Consultants
Yellow cells are for you to complete. Grey rows are a worked example for a concrete footing; replace them with the requirements of your specification. Point type: H = Hold, W = Witness, I = Inspection, R = Review.
Project | [5 empty] | ITP number
Client | [5 empty] | Revision / date
Activity / lot | [5 empty] | Prepared by
Specifications and drawings | [5 empty] | Approved by (client / superintendent)
Item | Activity / inspection or test | Acceptance criteria | Reference (spec, drawing, standard) | Verification method | Frequency | Point type | Responsibility | Record / evidence | Contractor sign-off | Client sign-off | Date
1 | Pre-start: approved drawings, specification and this ITP issued to the site team | Current revision on site; team briefed | Contract documents | Document check | Once, before work starts | R | Site supervisor | Drawing register, toolbox record
2 | Set-out of footing | Within tolerance stated on the drawings | Drawings; survey specification | Survey check | Each footing | I | Surveyor | Survey record
3 | Excavation: dimensions, depth and founding material | As shown on drawings; founding material accepted by the engineer | Drawings; geotechnical report | Measure and inspect | Each footing | H | Engineer | Inspection record, photos
4 | Reinforcement: bar size, spacing, cover and laps | As shown on drawings; cover as specified | Drawings; AS 3600 as called up | Visual inspection and measure | Each pour | H | Engineer | Signed release before pour
5 | Concrete delivery: grade and slump on each docket | Matches the specified grade and slump | Specification; AS 1379 | Check delivery dockets | Each truck | I | Site supervisor | Delivery dockets
6 | Concrete testing: slump and test cylinders | As specified | Specification; AS 1012 test methods | Sample and test by testing laboratory | As specified, e.g. per pour or per volume | W | Testing laboratory | Test reports
7 | Placement, compaction and finishing | No segregation or honeycombing; finish as specified | Specification | Visual inspection | Each pour | I | Site supervisor | Pour record
8 | Curing | Method and duration as specified | Specification | Visual check | Daily during curing | I | Site supervisor | Pour record
9 | Final inspection and records complete | All items signed off; test results conform; any nonconformances closed | This ITP | Review of records | At completion | R | Project engineer | Completed ITP and records